## Slide 1
Action Register – Key Actions and Accountabilities
Tracking critical actions, owners and timelines to ensure effective execution and accountability.
This register captures the priority actions required to implement our operating model and realize the expected benefits.
No.
Action
Owner
Due Date
Priority
Status
Progress
Comments / Next Step
01
Finalize target operating model design
and capability definitions
Operating Model
Lead
24 May 2025
High
In Progress
70%
Draft complete; stakeholder
review in progress.
02
Standardize and document priority
end-to-end processes
Process Lead
07 Jun 2025
High
In Progress
55%
Process mapping complete for
5 of 8 processes.
03
Define governance framework and
decision rights
Governance Lead
14 Jun 2025
High
Not Started
0%
Governance council kickoff
scheduled.
04
Implement integrated technology
platforms and interfaces
Technology Lead
28 Jun 2025
Medium
In Progress
40%
Interface build in progress;
UAT planning underway.
05
Establish data governance and
quality standards
Data Lead
21 Jun 2025
Medium
In Progress
60%
Data quality rules defined;
validation in progress.
06
Build partner and supplier
management framework
Partnership Lead
12 Jul 2025
Medium
Not Started
0%
Supplier segmentation
complete.
07
Develop change management and
communication plan
Change Lead
19 Jul 2025
Medium
In Progress
35%
Change impact assessment
underway.
Summary
Total Actions
7
Not Started
2 (29%)
In Progress
4 (57%)
Completed
1 (14%)
Overdue
0 (0%)