## Slide 1
Implementation roadmap
A three-phase plan will sequence the transformation from diagnosis to scaled execution.
01
Diagnose
Weeks 1–4
Objective: Establish the fact base and
prioritize value pools.
Activities
▪
Assess current-state processes and controls
▪
Quantify pain points and value leakage
▪
Confirm scope, governance and success metrics
Deliverable: Prioritized opportunity baseline
02
Design
Weeks 5–10
Objective: Define the future-state model
and implementation plan.
Activities
▪
Design target operating model and workflows
▪
Prioritize use cases, enablers and quick wins
▪
Develop business case, roadmap and
change approach
Deliverable: Target-state blueprint and
business case
03
Deploy
Weeks 11–20
Objective: Implement priority changes and
embed adoption.
Activities
▪
Launch pilot initiatives and governance routines
▪
Track KPIs, risks and benefit realization
▪
Scale successful interventions across the model
Deliverable: Activated roadmap and
measured impact
A phased approach reduces execution risk while accelerating value capture and organizational adoption.